## Risk_Assess_Portrait
Hazard | Consequence | Consequence Description | L | C | Risk Ranking | Mitigation Measures
Unable to secure a product transport route | Unable to transport product to market | No agreements with TasRail, Tasports etc | 2 | 5 | 10 | Negotiate agreements with port, rail and road authorities. Potential sites to be identified. Loading facilities at transfer points to be designed and costed
Unable to obtain mining approvals | Unable to mine | MRT, EPA do not grant necessary permits/approvals | 3 | 5 | 15 | Commence approval process as soon as practicable. Ensure scope of work covers all permitting requirments. Commence discussions with MRT, EPA, council and other stakeholders
Poor project management | Cost and timing overrun | Timelines, deadlines etc underestimated | 3 | 4 | 12 | Develop detailed project management plan. Appoint qualified project manager
Poor quality of technical data (Drilling, geotechnical data etc) | Poor geological model, pit design and other technical designs | Innaccurate assessment of resoucrses, product quality and financial model | 3 | 4 | 12 | Clearly define data requirements and laboratory reporting requirements. Identify additional drilling and testing plan.
Poor coal quality data (Materials handling, quality etc) | Unsuitable blending plans and materials handling design | Poor product quality and unsuitable handling characteristics | 3 | 5 | 15 | Clearly define data requirements and laboratory reporting requirements for materials handling equipment design
Unable to access sufficient water supply | Insufficient water for mine operations, high dust levels | Unable to draw water from Meadowbank Lake, insufficient onsite dam capacity | 2 | 5 | 10 | Confirm water supply with local/state governments. Design appropriate onsite water storage. Purchase water licences from local irregators
Unable to mine under powerlines | Loss of coal resources | Not obtaining approval/developing a management plan with Transend | 2 | 3 | 6 | Confirm restrictions with Transend and develop a management plan. Obtain approval for plan.
Key:
L = Likelihood
C = Consequence