## Page 1
|  | Prod Hrs | [5 empty] | Misc Hrs | [17 empty] | Hire |  | Zonge Hours
DATE | Mobe | 6 man | 5 man | 4 man | 3 man | 2 man | 1 man | Travel (6 man) | Travel (5 man) | Travel (4 man) | Travel (3 man) | Travel (2 man) | Travel (1 man) | Standby (6 man) | Standby (5 man) | Travel (3 man) | Standby (3 man) | Standby (2 man) | Standby (1 man) | Weather (6 man) | Weather (5 man) | Weather (4 man) | Weather (3 man) | Weather (2 man) | Weather (1 man) |  | Vehicle |  | Comments
2018-02-28 | 10.5 | [27 empty] | Mobilisation from Adelaide to Strahan - overnight
2018-03-01 | [16 empty] | 5 | [11 empty] | On Standby waiting for equipment to arrive
2018-03-02 | [16 empty] | 10 | [11 empty] | Loading swing load for chopper and setting up tents
2018-03-03 |  |  |  |  | 11 | [23 empty] | JSA and Toolbox meeting, Prep remote pits and deploying Tx wire
2018-03-04 |  |  |  |  | 11.5 | [22 empty] | 1.5 | Prep second remote pit, carrying water and deploying Tx wires
2018-03-05 |  |  |  |  | 11 | [22 empty] | 0.5 | Deploy RX cables / pots and Acquired data
2018-03-06 |  |  |  |  | 11 | [22 empty] | 1 | Acquired data
2018-03-07 |  |  |  |  | 11 | [22 empty] | 0.5 | Pack up line 5285800 and setup line 370300
2018-03-08 |  |  |  |  | 11.5 | [22 empty] | 0.5 | Finish setup and acquired data
2018-03-09 |  |  |  |  | 11 | [22 empty] | 0.5 | Acquire data, Pack up line 370300 move to next line 370150 and setup
2018-03-10 |  |  |  |  | 11.5 | [22 empty] | 0.5 | Setup and acquired data onLine 370150
2018-03-11 |  |  |  |  | 11 | [22 empty] | 0.5 | Acquired data, Pack up line and setup next line
2018-03-12 |  |  |  |  | 11 | [22 empty] | 0.5 | Setup and acquire data on Line 369850
2018-03-13 |  |  |  |  | 11 | [22 empty] | 0.5 | Acquired data on Line 369850, Pack up the line and setup next line
2018-03-14 |  |  |  |  | 11.5 | [22 empty] | 0.5 | Setup and Acquired data on Line 369550
2018-03-15 |  |  |  |  | 11 | [22 empty] | 0.5 | Acquired data and pack up LIne halfway
2018-03-16 |  |  |  |  | 11.5 | [22 empty] | 0.5 | Pack up, setup and Acquired data
2018-03-17 |  |  |  |  | 12 | [22 empty] | 0.5 | Acquired data and pack up line halfway
2018-03-18 |  |  |  |  | 10 | [22 empty] | 0.5 | Pack up cables and tx wires
2018-03-19 |  |  |  |  | 10.5 | [22 empty] | 0.5 | Packing up
2018-03-20 | [16 empty] | 11.5 | [11 empty] | Packing up - Chopper gear to Strahan and Pack in storage
2018-03-21 | [10 empty] | 8.5 |  |  |  |  | 8.5 | 1.5 | [11 empty] | Finish Packing away gear - Travel to Devonport - Fly to Adelaide
TOTAL HOURS
TOTALS
| Mobe | 6 man | 5 man | 4 man | 3 man | 2 man | 1 man | Travel (6 man) | Travel (5 man) | Travel (4 man) | Travel (3 man) | Travel (2 man) | Travel (1 man) | Standby (6 man) | Standby (5 man) | Travel (3 man) | Standby (3 man) | Standby (2 man) | Standby (1 man) | Weather (6 man) | Weather (5 man) | Weather (4 man) | Weather (3 man) | Weather (2 man) | Weather (1 man) |  | Vehicle | Zonge Hours
Sub Totals | 10.5 | 0 | 0 | 0 | 189 | 0 | 0 | 0 | 0 | 0 | 8.5 | 0 | 0 | 0 | 0 | 8.5 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5
Totals | 10.5 | 0 | 0 | 0 | 189 | 0 | 0 | 0 | 0 | 0 | 8.5 | 0 | 0 | 0 | 0 | 8.5 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5
Rate p/hr | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Billable Total | [17 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0